## Engineer
City of Cleveland
Mayors Office of Capital Projects
Project Closeout Checklist
Project: |  |  |  |  | CT No: |  | CT 0103 PI2017000000030
Contractor: |  |  |  |  | Project No: |  | C15-301
NTP Date: |  |  | Contract Duration: | 43384 | Contract Completion Date: |  |  | 2018-10-11
Not Needed | Complete | Close Out Initiation |  |  | Responsibility
[5 empty] | PM | E/A | Contractor | ECCS | Finance | OEO
Project Acceptance (3% Retainage Release)
|  | Notice of Substantial Completion |  |  |  |  | X
|  | Final Quantity and Change Order Reconciliation |  |  | X
|  | Punch list Acceptance (Date: 12/05/2018) |  |  |  |  | X
|  | As Build Record Drawings |  |  |  |  | X
|  | Arch./Eng of Record Project Acceptance Letter |  |  |  | X
|  | Final Affidavit of Compliance Prevailing Wages |  |  |  |  | X
|  | OEO Retainage Release Letter | [7 empty] | X
|  | OEO Final Affidavit of Compliance Form | [7 empty] | X
|  | Utility Video Inpsection | [5 empty] | X
|  | Operation & Maintenance Manual (if needed) |  |  |  |  | X
|  | Certificate of Occupancy (C of O) (if needed) |  |  |  |  | X
|  | Close Regulatory Permits (if needed) |  |  |  |  | X
|  | Change over locks & transmit keys to Owner (if needed) |  |  |  |  | X
|  | Proof of temp utilities paid w/ meter readings (if needed) |  |  |  |  | X
Final Acceptance (2% Retainage Release)
|  | Warranty Punch list Acceptance (Date: 12/05/2018) |  |  |  |  | P
Final Construction Report Form
|  | Arch./Eng of Record Project Acceptance Letter |  |  | S | P |  | S
|  | Final Affidavit of Compliance Prevailing Wages |  |  | S |  | P |  | S
|  | OEO Retainage Release Letter | [6 empty] | S | P
|  | Performance Review Forms |  |  | P
Legend:
PM | Project Manager
E/A | Engineer or Architect of record
Finance | Sr. Budget Analyst
ECCS | E&C Construction Section
DPS | Division of Purchases & Supplies
OEO | Ohio Equal Employment

## Architect
City of Cleveland
Mayors Office of Capital Projects
Project Closeout Checklist
Project: |  |  | 2018 Mohican Park Half Basketball Court |  |  | CT No: | PI201900000005
Contractor: |  |  | R.J. Platten Contracting |  |  | Project No: | Project #
NTP Date: |  |  | 2019-03-08 | Contract Duration: | # | Contract Completion Date: |  |  | 2019-08-02
N/A | Complete | Tasks |  | Notes | Responsibility
[5 empty] | PM | AoR/EoR | Contractor | OEO | Finance
SUBSTANTIAL COMPLETION (Part C, Paragraph C-11.H.2)
| X | 1 | When the Contractor considers that the Work, or a designated portion thereof which is acceptable to the City, is substantially complete, the Contractor shall prepare for submission to the City a list of items (“Contractor’s Punch-List”) which in his opinion are to be completed or corrected and shall request in writing that the Architect perform a Substantial Completion inspection. |  |  |  | X
X |  | 2 | Final Cleaning |  |  |  | X
| X | 3 | The Architect shall review the Contractor's Punch-List and shall compile a City’s Punch-List of items to be corrected and completed. The failure to include any items on such list does not alter the responsibility of the Contractor to complete all Work in accordance with the Contract Documents. |  |  | X
| X | 4 | The Architect will then make an inspection to determine the status of completion. |  |  | X
X |  | 5 | If the Architect determines that the Work is not substantially complete, he will notify the Contractor, in writing, listing the reasons, and: |  |  | X
X |  | a | The Contractor shall correct all items listed and send a second written notice of substantial completion to the Architect. |  |  |  | X
X |  | b | The Architect will re-inspect the Work. |  |  | X
| X | 6 | When the Architect on the basis of an inspection determines that the Work or designated portion thereof is Substantially Complete, he will then prepare a Certificate of Substantial Completion. |  |  | X
X |  | 7 | The punch list shall fix the time within which the Contractor shall complete the items listed therein. |  |  |  | X
X |  | 8 | The Contractor shall obtain from the Authority Having Jurisdiction a Certificate of Occupancy for the Work, or a designated portion thereof which is acceptable to the City. |  |  |  | X
X |  | 9 | The date of Substantial Completion shall be established as the date of the Certificate of Substantial Completion or the Certificate of Occupancy, whichever is later. |  | X
FINAL ACCEPTANCE (Part C, Paragraph C-11.H.3)
| X | 1 | Substantial Completion. |  |  |  | X
X |  | 2 | Advise City of pending insurance changeover requirements. |  |  |  | X
X |  | 3 | Submit record drawings and specifications, maintenance manuals, warranties, and similar record information (3 hard copies, 1 electronic copy). |  |  |  | X
X |  | 4 | Deliver spare parts, extra stock, and similar items. |  |  |  | X
X |  | 5 | Change over locks and transmit keys to City. |  |  |  | X
X |  | 6 | Complete start-up testing of systems and instruction of City’s operation and maintenance personnel. |  |  |  | X
| X | 7 | Remove temporary facilities and controls. |  |  |  | X
| X | 8 | Complete final clean-up. |  |  |  | X
| X | 9 | Touch-up, repair, and restore marred, exposed finishes. |  |  |  | X
X |  | 10 | Submit record drawings to Architect for the Architect’s preparation of as-built drawings. | Architect Complete |  |  | X
| X | 11 | Submit final payment request with releases of liens from all subcontractors and suppliers and supporting documentation. Include insurance certificates. |  |  |  | X
| X | 12 | Submit a copy of the Punch-List stating that each item has been completed or otherwise resolved for acceptance. |  |  |  | X
X |  | 13 | Submit final meter reading for utilities, a record of stored fuel, and similar date as of the date of Substantial Completion. |  |  |  | X
|  | 14 | Submit consent of surety to final payment. |  |  |  | X
| X | 15 | Final Inspection walk-through |  | X | X
X |  | 16 | Training for City Personnel |  |  |  | X
FINAL COMPLETION (Part C, Paragraph C-11.H.4)
|  | 1 | Final Guarantee Inspection |  | X | X | X
FINAL PAYMENT AFTER THE GUARANTEE PERIOD (Part C, Paragraph C-11.I)
|  | 1 | An affidavit that all payrolls, bills for materials and equipment, and other indebtedness, including, but not limited to, liens connected with the Work for which the City might in any way be responsible, have been paid or otherwise satisfied; |  |  |  | X
|  | 2 | Consent of surety, if any, to final payment; |  |  |  | X
|  | 3 | If required by the Architect, other data establishing payment or satisfaction of all such obligations, such as receipts, releases, and waivers of liens arising out of the Contract, to the extent and in such forms as may be designated by the Architect. |  |  |  | X
|  | 4 | A written certification by the Contractor that: |  |  |  | X
|  | a | The Contractor has reviewed the requirements of the Contract Documents; |  |  |  | X
|  | b | The Work has been inspected by the Contractor for compliance with all requirements of the Contract Documents; |  |  |  | X
|  | c | The Work complies in all aspects with the requirements of the Contract Documents; |  |  |  | X
|  | d | All equipment and systems have been installed in accordance with the Contract Documents and have been tested in accordance with Specification requirements and are operational, and |  |  |  | X
|  | e | The Work is complete in all respects. |  |  |  | X
Legend:
PM | Project Manager
E/A | Engineer or Architect of record
Finance | Sr. Budget Analyst
DPS | Division of Purchases & Supplies
OEO | Ohio Equal Employment